## Sheet1
Project Title
Boston Student Housing
WEEK 1 |  |  | Reghunaath
Task | Status | Handled by | Neha
Prepare a project plan | Completed | Team | Krishnan
Data collection and mining | Completed | Reghunaath | Team
Analyse the feasibility of StreamLit | Completed | Neha
Analyse the feasibility of Plotly | Completed | Krishnan
Make a submission for this iteration | Completed | Team | Completed
Organize the scrapped data | In Progress | Reghunaath | In Progress
To do
END OF THE WEEK TEAM MEETING (10/12/2024)
WEEK 2
Task | Status | Handled by
Preprocessing the organized data | To do | Neha
Setup the necessary tools for using plotly | To do | Krishnan
Setup the testing methodologies | To do | Reghunaath
Verify the Preprocessed data | To do | Krishnan
Save the Final data and upload it to the repository | To do | Neha
END OF THE WEEK TEAM MEETING (10/19/2024)
WEEK 3
Task | Status | Handled by
Create a plot between various features of the data in order to understand the underlying patterns and trends | To do | Neha
Understand the data | To do | Team
Decide the features that needs to be included in the final dashboard | To do | Team
Create Feature plots for the same | To do | Reghunaath
Export each and every plot into HTML | To do | Reghunaath
Update everything in technical report | To do | Krishnan
END OF THE WEEK TEAM MEETING (10/26/2024)
WEEK 4
Task | Status | Handled by
Create a dashboard using Plotly.Dash/StreamLit | To do | Krishnan
Check if the plots can be incorporated without any errors | To do | Neha
If so, do the necessary reformatting | To do | Reghunaath
Finalize and cross verify the plots | To do | Neha
Discuss the features of the dashboard | To do | Team
END OF THE WEEK TEAM MEETING (11/02/2024)
WEEK 5
Task | Status | Handled by
Start the presentation work and update the progress so far | To do | Neha
Check the feasibility of incorporating the features into the dashboard | To do | Krishnan
Finalize the features | To do | Team
Start Incorporating the features one by one | To do | Krishnan
Update the GitHub Repository | To do | Reghunaath
(Potential Mid-Terms week. (11/02-11/09))
END OF THE WEEK TEAM MEETING (11/16/2024)
WEEK 6
Task | Status | Handled by
Start doing the Dashboard | To do | Krishnan
Decide troubleshooting framework | To do | Reghunaath
Update the PPT | To do | Neha
Carry out a certain feature of the dashboard | To do | Reghunaath
Carry out a certain feature of the dashboard | To do | Neha
Update the Technical report | To do | Neha
Finish the Dashboard | To do | Krishnan
Verify the working of dashboard | To do | Neha
Incorporate tesing methodologies | To do | Reghunaath
Make changes to the dashboard accordingly(if any) | To do | Krishnan
Update the GitHub Repository | To do | Neha
Prepare the final PPT | To do | Neha
END OF THE WEEK TEAM MEETING (11/23/2024)
WEEK 7
Task | Status | Handled by
Check the final version of documents | To do | Team
End to end testing | To do | Team
Upload all the project files to the GitHub repository | To do | Team
Prepare for the presentation | To do | Team
Check if the project is ready for submission | To do | Team
FINAL TEAM MEETING (11/30/2024)